## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Dark
PROJECT TITLE
Company name | Petroc Fdsc Computing Year 2 |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Chaz Goddard
Project Start Date: | 2021-11-01 |  |  |  |  | November | [13 empty] | December | [27 empty] | January
Scrolling Increment: | 21 | time axis 2021-11-22 to 2022-01-16
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Project Kick off
project overview |  | All |  | 2021-11-01 | 1
Role Assignment |  | All |  | 2021-11-01 | 1
Agree meet days |  | All |  | 2021-11-01 | 1
setup Communication and project tools |  | P.M/T.A |  | 2021-11-01 | 1
Completion of project kick off | Milestone | All |  | 2021-11-05 | 1
Framework Research
Back-End Research |  | B.E.D |  | 2021-11-08 | 28
Front-End Research |  | F.E.D |  | 2021-11-08 | 28
Documentation Research |  | T.A |  | 2021-11-08 | 28
Rearch Share | Goal | All |  | 2021-12-06 | 1 | M: 2
White Box Cenceptulisation
Database Concept | Low Risk |  |  | 2021-12-07 | 11
Browser portal Concept | Low Risk |  |  | 2021-12-07 | 11
X Mas Break | High Risk | All |  | 2021-12-18 | 14
Database Concept creep | Low Risk |  |  | 2022-01-03 | 5
Browser portal Concept creep | Low Risk |  |  | 2022-01-03 | 5
TITLE 4
Task 1 |  |  |  | 2022-01-06 | 15
Task 2 |  |  |  | 2022-01-20 | 5
Task 3 | Milestone |  |  | 2022-03-03 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one